## Sheet1
| Plan | [5 empty] | Actual Effort
| Planned | Actual | Planned | Actual | Assigned | Estimated | Name of | Actual | Sign-off
Work Tasks | Start | Start | Complete | Complete | Developer | Hours | Developer | Hours | (Name) | Comments
Case 1 - Customer Reservation
MILESTONE 1 |  |  | 2002-07-31 | 2002-08-04
Case 2 - Dispatch Cab
TO BE COMPLETED
Code/Testing
Tsunami
End-to-end acceptance test | 2002-08-06 | 2002-08-06 | 2002-08-07 |  | John | 2
MIKAM Tribe
End-to-end acceptance test | 2002-08-06 | 2002-08-06 | 2002-08-07 |  | Alex | 2
Team Doug
Change zone ID starting at 1 rather than 0 | None | 2002-08-07 | 2002-08-07 |  |  | 1
End-to-end acceptance test | 2002-08-06 | 2002-08-06 | 2002-08-07 |  |  | 2
The SegFaults
Fix multiple request same zone, cab accepted twice. Need 1 thread per zone. Throws NULL pointer exception | None | 2002-08-07 | 2002-08-07 |  | Jesse | 4
End-to-end acceptance test | 2002-08-06 | 2002-08-06 | 2002-08-07 |  |  | 2
Masters
Handle rejected Cab ID. Loop log-in screen | None | 2002-08-07 | 2002-08-07 |  | Sabina | 4 |  | 6 | Sabina
Cab console print messages to Text area | None | 2002-08-07 | 2002-08-07 |  | Belen | 4 | Belen | 4 | Belen
End-to-end acceptance test | 2002-08-06 | 2002-08-06 | 2002-08-07 |  |  | 2
MILESTONE 2 | 2002-08-05 | 2002-08-05 | 2002-08-07 |  |  | 23
Case 4 - Drop Off Customer
TO BE COMPLETED
Tsunami
None | [5 empty] | 0
MIKAM Tribe
Update cab info when updateModelInfo is called. | [5 empty] | 2
Team Doug
Write rideHasFinished() | 2002-08-06 |  | 2002-08-09 |  |  | 3
Statistics issues with above | [5 empty] | 1
Integrate our methods with the system | [5 empty] | 1
The SegFaults
Masters
Code/Testing
CabConsoleImplementation |  |  |  |  | Belen |  | Belen | 4.5 | Belen
RMI Testing on CabConsole |  |  |  |  | Belen |  | Belen | 1.5 | Belen
CabConsoleImplementation |  |  |  |  | Takako |  | Takako | 5 | Takako
CabConsoleImplementation |  |  |  |  | Takako |  | Takako | 10 | Takako
CabConsoleGUI&CabConsole |  |  |  |  | Takako |  | Takako | 4 | Takako | Made overall changes when status changes from 2 to 4. Made changes to functionality while coding unit test
GPS Test code |  |  |  |  | Takako |  | Takako | 1 | Takako
CabConsoleGUI&CabConsole |  |  |  |  | Sara |  | Sara | 2 | Sara
CabConsoleImplementation |  |  |  |  | Sara |  | Sara | 5.5 | Sara
RMI Testing on CabConsole |  |  |  |  | Sara |  | Sara | 1.5 | Sara
Treading |  |  |  |  | Sabina & Jesse |  | Sabina & Jesse | 2 | Sabina
Correcting RMI message to Model | [6 empty] | Sabina | 3 | Sabina
Testing Cab Console | [6 empty] | Sabina | 3 | Sabina
Testing entire system to prepare for prensentation to Valentine | [6 empty] | Sabina | 6 | Sabina
Documentation
Consoliding the documantation |  |  |  |  | Orit |  | Orit | 1.5
Total hours by Masters | [7 empty] | 51.5
MILESTONE 3 | 2002-08-07 | 2002-08-07 | 2002-08-09 |  |  | 7
System Startup
TO BE COMPLETED
Tsunami
Installation of executable using installer | None | 2002-07-28 |  |  | Dave | 8
Dynamic class loading of client files | None | 2002-07-31 |  |  |  | 4
MIKAM Tribe
Dynamic class loading of client files | None | 2002-07-31 |  |  |  | 4
Team Doug
Write/test getAllCabs | [5 empty] | 4
Write/test getAllZones | [5 empty] | 4
Write/test storeAllZones | [5 empty] | 4
The SegFaults
Mapper UI/DB Integration | 2002-08-07 | 2002-08-07 |  |  |  | 2
Zone poly control points | 2002-08-09 | 2002-08-09 |  |  |  | 6
Masters
MILESTONE 4 | 2002-08-05 | 2002-08-05 | 2002-08-12 |  |  | 36
Case 3 - Change/Cancel Customer
TO BE COMPLETED
Tsunami
None
MIKAM Tribe
Team Doug
The SegFaults
Masters
CabConsoleImplementation |  |  |  |  | Takako |  | Takako | 10 | Takako
CabConsoleGUI |  |  |  |  | Takao |  | Takako | 3 | Takako
CabConsoleUnitTest coding & testing |  |  |  |  | Takako |  | Takako | 3 | Takako
GPSUnitTest coding |  |  |  |  | Takako |  | Takako | 1 | Takako
Documentation | [7 empty] | 1 | Takako
RMI Testing on CabConsole |  |  |  |  | Sara |  | Sara | 1.5 | Sara | Made overall changes when status changes from 2 to 4. Made changes to functionality while coding unit test
Change/Cancel functionality |  |  |  |  | Sara |  | Sara | 2 | Sara | Made a little changes according to the change made in CanConsoleImplementation file
Time-out thread |  |  |  |  | Sara |  | Sara | 2 | Belen | Not done
[7 empty] | Belen | 3 | Belen | Haven't tested yet
Took screen shots of cab console fpr documentation
Currently working on this task
MILESTONE 5 | 2002-08-09 |  | 2002-08-12 |  |  | 0
Documentation
TO BE COMPLETED
Tsunami
MIKAM Tribe
Team Doug
The SegFaults
Masters
Consoliding the documantation |  |  |  |  | Orit |  | Orit | 1.5 | Orit
Updated Architecture |  |  |  |  | Orit |  | Orit | 1.5
Cab Console Technical Documentation |  | 2002-08-10 | 2002-08-11 |  | Orit |  | Orit | 4
Cab Console User Manual |  | 2002-08-11 | 2002-08-11 |  | Orit |  | Orit | 3
Total hours by Masters | [7 empty] | 11.5
MILESTONE 6 | [5 empty] | 0
Acceptance Test
TO BE COMPLETED
Tsunami
MIKAM Tribe
Team Doug
The SegFaults
Masters
MILESTONE 7 | [5 empty] | 0
Note on K60: Inplement CabConsole main
Note on K66: Modified GUI according to the change made in CabConsole
Note on K61: add RMI with the help of Tsunami team and test both way communication